## Team Roster
Stakeholders
Team |  | Stakeholder Name | Email | Address or Location | Variance from US Eastern Time Zone | Phone | Role/ Responsibility | RACI Chart |  |  |  | Core Team (Y/N)
| HR Team Number | [6 empty] | Responsible | Accountable | Consult | Inform
Integration Team - Lead | 10 |  |  |  | 0 | 614-538-4622 (office) | Team Lead |  | Team Level |  |  | Y
Integration Team - Deputy Team Lead | 4 |  |  |  | -3 | 925.872.2979 (Mobile) | Deputy Team lead | Team Level |  |  |  | Y
Sub Team 1 | 22 | [5 empty] | Sub Team 1 Lead |  | Sub Team Level |  |  | Y
Sub Team 1 | 1 |  |  |  | -1 | C: 612.414.5873 H: 952.432.9165 | Sub Team 1 Team Member | Sub Team Level
Sub Team 1 | 20 |  |  |  | -1 | 515-276-5914 | Sub Team 1 Team Member | Sub Team Level
Sub Team 1 | 23 |  |  |  | -1 | 901-212-1056 | Sub Team 1 Team Member | Sub Team Level
Sub Team 1 | 24 |  |  |  | 10.5 |  | Sub Team 1 Team Member | Sub Team Level
Sub Team 2 | 18 |  |  |  | -3 | 916-635-8005 | Sub Team 2 Lead |  | Sub Team Level |  |  | Y
Sub Team 2 | 11 |  |  |  | 10.5 | WP: 91-44-2254-9650 WF: 91-44-2254-0710 HP: 91-44-2442-2927 | Sub Team 2 Team Member | Sub Team Level
Sub Team 2 | 12 |  |  |  | 0 | Tel: 732-516-9001 | Sub Team 2 Team Member | Sub Team Level
Sub Team 2 | 13 |  |  |  | 10.5 | Phone #. 94480 52952 | Sub Team 2 Team Member | Sub Team Level
Sub Team 2 | 5 |  |  |  | 0 | 610-657-0172 (C) | Sub Team 2 Team Member | Sub Team Level
Sub Team 2 | 21 |  |  |  | 12 |  | Sub Team 2 Team Member | Sub Team Level
Sub Team 2 | 6 |  |  |  | 10.5 | Tel No.: 044 – 42021023 Mobile: 0-9840527704 | Sub Team 2 Team Member | Sub Team Level
Sub Team 3 | 15 |  |  |  | 10.5 | +919885481436 +919885903764 +914039181520 | Sub Team 3 Lead | Sent email to confirm role 5/16/06 | Sub Team Level |  |  | Y
Sub Team 3 | 18 |  |  |  | -1 | Tel. 847-706-6797 Fax 847-706-6729 | Sub Team 3 Team Member | Sub Team Level
Sub Team 3 | 2 |  |  |  | 0 | 302-366-1088 (Res | Sub Team 3 Team Member | Sub Team Level
Sub Team 3 | 25 | [5 empty] | Sub Team 3 Team Member | Sub Team Level
Sub Team 3 | 14 |  |  |  | 0 |  | Sub Team 3 Team Member | Sub Team Level
Sub Team 3 | 28 |  |  |  | -1 |  | Sub Team 3 Team Member | Sub Team Level
Sub Team 3 | 29 | [5 empty] | Sub Team 3 Team Member | Sub Team Level
Sub Team 3 | 30 | [5 empty] | Sub Team 3 Team Member | Sub Team Level
Sub Team 4 | 8 |  |  |  | 0 | (703) 542 – 6374 (H) | Sub Team 4 Lead |  | Sub Team Level |  |  | Y
Sub Team 4 | 16 |  |  |  | ? | (W) 809-563-0530 | Sub Team 4 Team Member | Sub Team Level
Sub Team 4 | 9 |  |  |  | -3 |  | Sub Team 4 Team Member | Sub Team Level
Sub Team 4 | 19 |  |  |  | 0 |  | Sub Team 4 Team Member | Sub Team Level
Sub Team 4 | 7 |  |  |  | 0 | (703) 453-9135 (H) (301) 807-4394 (C) | Sub Team 4 Team Member | Sub Team Level
Sub Team 4 | 27 | [5 empty] | Sub Team 4 Team Member | Sub Team Level
Sub Team 4 | 31 | [5 empty] | Sub Team 4 Team Member | Sub Team Level
HR Team |  |  |  |  | 10.5 |  | HR Team Rep to the Integration Team |  |  |  | Team Level | Y
HR Team |  |  |  |  | 10.5 |  | HR Team Rep to the Integration Team |  |  |  | Team Level | Y
Core Team | [6 empty] | Project Manager |  | Project Level |  |  | Y
Core Team | [6 empty] | Deputy Project manager | Project Level |  |  |  | Y
Core Team | [6 empty] | Chapter 1 Lead | Project Level |  |  |  | Y
Core Team | [6 empty] | Chapter 2 lead | Project Level |  |  |  | Y
Core Team | [6 empty] | Chapter 3 Lead | Project Level |  |  |  | Y
Core Team | [6 empty] | Chapter 4 Lead | Project Level |  |  |  | Y
Core Team | [6 empty] | Edit Team Lead | Project Level |  |  |  | Y
Core Team | [5 empty] | 614-538-4622 (office) | Integration Team Lead | Project Level |  |  |  | Y
Core Team | [6 empty] | HR Team Lead | Project Level |  |  |  | Y
Withdrawn | [6 empty] | Withdrew from team | Contributor Withdrew
Withdrawn | [6 empty] | Withdrew from team | Contributor Withdrew
Withdrawn |  |  |  |  | 0 |  | Withdrew from team | Contributor Withdrew
Reassigned |  |  |  |  | 10.5 | 91-9886897808 | Reassigned as a reviewer | Reassigned as a reviewer
Removed | [6 empty] | No response | Sent email to confirm interest on 5/8/06

## Dependencies
# | Source Project | Source Document for Project Inputs | Location Of Document | Output Deliverables | External Point of Contact | Project Point of Contact | Priority | Number of Resources | Date Expected | Target Project for Outputs from This Project | Comments | Done
1 | PMI Standards | PMBOK 3rd Edition | Bluestep - Key Reference documents | Skills, knowledge, vocabulary, and structure | N/A | Team 1 | 1 |  | Current | PMCDFU | Align with structure, vocabulary, and skills. Should also consider the PMBOK erratta sheets posted on PMI.ORG.
2 | PMI Standards | PMCDF - Currrent version | Bluestep - Key Reference documents | Structure, categories, vocabulary | N/A | Team 2 | 1 |  | Current | PMCDFU | Align with chapter structure and document structure (size limits relative to previous document)
3 | PMI Standards | PM Role Delineation Study | Bluestep - Key Reference documents | Skills, knowledge listings | N/A | Team 2 | 2 |  | Current | PMCDFU | Key document. We need to align with the research indicating required knowledge and skills, and other research data.
4 | PMI Standards | PMP Exam Specifications | Bluestep - Key Reference documents | Skills, knowledge listings | N/A | Team 2 | 1 |  | Current | PMCDFU | Key document. We need to align with the required knowledge and skills described.
5 | PMI Standards | OPM3 | Bluestep - Key Reference documents (not printable) | Best practice categories | N/A | Team 3 | 1 |  | Current | PMCDFU | Need to align with best practices and capabilities. I assume there is some hierarchy to the OPM3. We need to choose and define the base project manager and the level competency that they should attain (e.g., per the current PMCDF, would a PMP - 3 year experience project manager be expected to be competent in all described domains?).
6 | PMCDFU | PM Career Framework | Bluestep - Key Reference documents | Raise issues if not in alignment | Roecker | Team 3 | 2 |  | Current |  | Initiative underway through PMI Education.
7 | PMI Standards | Project Management Experience and Knowledge Self-Assessment Manual | http://pmi.books24x7.com/toc.asp?bookid=5608 | Guidance only | N/A | Team 3 | 3 |  | Current | PMCDFU | This standard was published in 2000. It does not appear to have been updated since
8 | Standards Team | Unified Project Manaagement Lexicon | Not yet available - Info at http://www.pmi.org/prod/groups/public/documents/info/pp_pmlexiconproject.asp | Vocabulary | TBD | Team 4 | 2 |  | TBD | PMCDFU | I believe this is a new standards team that is just starting up. This is the next generation of the Combined Standards Glossary.
9 | PMI Standards | Combined Standards Glossary - Second Edition | Bluestep - Key Reference documents | Vocabulary | N/A | Team 4 | 1 |  | Current | PMCDFU | Align with vocabulary
10 | PMI Standards | PMi Code of Conduct - Existing | Bluestep - Key Reference documents | Raise issues if not in alignment | N/A | Team 4 | 1 |  | Current | PMCDFU | Particularly in the personal competence dimensions
11 | PMI Standards | PMI Code of Conduct - Exposure Draft | Bluestep - Key Reference documents | Raise issues if not in alignment | TBD | Team 4 | 2 |  | TBD | PMCDFU | Particularly in the personal competence dimensions. Not likely to be timely. Rely primarly on the current.
12 | PPMS | Program Management Standard | Must be logged in as a member to see drafts available at - https://secure.pmi.org/memberapp/code/premium_content/standards/index.asp | Vocabulary and structure |  | Team 4 | 2 |  | Current | PMCDFU | Exposure drafts are available, but not final copy. Probably will not get final.
13 | PPMS | Portfolio Management Standard | Must be logged in as a member to see drafts available at - https://secure.pmi.org/memberapp/code/premium_content/standards/index.asp | Vocabulary and structure |  | Team 4 | 2 |  | Current | PMCDFU | Exposure drafts are available, but not final copy. Probably will not get final.

## Communications Plan
Communication # | Organization or Team | Who Gets Message? | Message | Who Sends It? | Form Of Message | Frequency / Date | Completed On | Comments
1 | Ingegration Team | Integration Team members | Kickoff Meeting | Mike Reed | Presentation | 2006-05-01 | 2006-05-04 | Posted on bluestep
2 | Deputy & Sub Team Leads | Prospective Deputy & Leads | Invitation to be Deputy & Leads | Mike Reed | Email | 2006-05-01 | 2006-05-04
3 | Core Team | Core Team | Status of Integration Team Deliverables | Mike Reed | Verbal | Weekly | Started in April | Core team meets weekly with a few exceptions
4 | Integration Team Lead and Deputy Lead | Mike Reed and Roberta Bonsall | Status of Sub Team Deliverables | Sub Team Leads | Email | Weekly | Started on May 22
5 | Ingegration Team | All Team members | Chapters are available for review of alignment with PMI standards as assigned to each sub team | Mike Reed | Email | Once available for two cyles |  | Expect some time in first week of June and first week of August with 30 days to review and return comments to the chapter teams
6 | Ingegration Team | All Team members | Availability of external Exposure draft | Mike Reed | Email | As available |  | Expected to be available at end of September and comments accepted for two months
7 | Ingegration Team | All Team members | Instant Message | Mike Reed | IM | For team meetings | Sent on 5/23/06 and used consistently there after | Helps especially when there is no webinar capability and some team members have to be dialed into meetings
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
15
26
16
17
18
19
20
31
39 | Project Teams | Other process teams | Extended program management meeting | Team leads or owners | 5 Minute presentation | Weekly | Starting 4/19/05 | Once a month, extend the program management team meeting to include all folks, and a 10 minute discussion of what each team is doing.
Michael Reed, Roberta Bonsall, kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Joan Barnes-Weatherton, Priyesh Gopalakrishnan, Sreedharan Nair, Louisa Andrianopolulou, Nathaniel Barksdale, Raja Sekhar, Michael Hatheway, Cindy Beck, Juan Monroy, Indira Prasad, Rocco Tellier, Lee Towe, Sanina Shen, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, Rachna Sharma, David Cobb, Gethsemani Palacios
Roberta Bonsall
Kumar P.V.S.
Richard Bates
Bernard Anthony Holmes
Terry Boyd
Joan Barnes-Weatherton
Priyesh Gopalakrishnan
Sreedharan Govindan Nair
Louisa Amalia Andrianopoulou
Nathaniel Barksdale, Jr.
Nerella Raja Sekhar
Michael Hatheway
Cindy Beck
Juan Monroy
Indira Prasad
Rocco Tellier
Lee Towe
Sanina Shen
Krishna Mohan Malladi
Xiaosong (David) Liu
Cindy Archer-Burton
Prem Kiran Udayavarma
Rachna Sharma
David Cobb
Gethsemani Palacios

## Team Meetings
Meeting # | Status | Date | Time | Expected Duration | Actual Duration | Meeting Owner | Invited Participants | Actual Participants | Absent | Active Via Email or Other Means | Meeting Purpose | Agenda | Minutes
1 | Closed | 2006-05-04 | 10 PM EDT | 1 hr | 1 HR | MR | Michael Reed, Roberta Bonsall, kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Priyesh Gopalakrishnan, Sreedharan Nair, Louisa Andrianopolulou, Nathaniel Barksdale, Raja Sekhar, Michael Hatheway, Cindy Beck, Juan Monroy, Indira Prasad, Rocco Tellier, Lee Towe, Sanina Shen, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, Rachna Sharma, David Cobb, Gethsemani Palacios | Michael Reed, Roberta Bonsall, Cindy Beck, Rocco Tellier, Sanina Shen, Rachna Sharma, Sreedharan Nair, | Kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Joan Barnes-Weatherton, Priyesh Gopalakrishnan, Louisa Andrianopolulou, Nathaniel Barksdale, Raja Sekhar, Michael Hatheway, Juan Monroy, Indira Prasad, Lee Towe, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, David Cobb, Gethsemani Palacios | Not tracked | Team Orientation and Project Kickoff | Kick off presentation Slide deck distributed | No minutes were taken as the slides constituted the entire meeting.
2 | Closed | 2006-05-08 | 10 PM EDT | 1 hr | 1 hr | MR | Michael Reed, Roberta Bonsall, kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Joan Barnes-Weatherton, Priyesh Gopalakrishnan, Sreedharan Nair, Louisa Andrianopolulou, Nathaniel Barksdale, Raja Sekhar, Michael Hatheway, Cindy Beck, Juan Monroy, Indira Prasad, Rocco Tellier, Lee Towe, Sanina Shen, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, Rachna Sharma, David Cobb, Gethsemani Palacios, Scott Bable | Michael Reed, Roberta Bonsall, Sreedharan Nair, Nathaniel Barksdale, Cindy Beck, Indira Prasad, Rocco Tellier, Sanina Shen, Scott Bable | kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Joan Barnes-Weatherton, Priyesh Gopalakrishnan, Louisa Andrianopolulou, Raja Sekhar, Michael Hatheway, Juan Monroy, Lee Towe, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, Rachna Sharma, David Cobb, Gethsemani Palacios | Not tracked | Establish common understanding of what alignment means for major documents | Agenda 1. Role call (5 minutes) 2. Survey and team membership (5 minutes) 3. Discussion of alignment to the PMBOK (10 minutes) 4. Discussion of alignment to the PMP Exam Specs (10 minutes) 5. Discussion of alignment to the OPM3 (10 minutes) 6. Discussion of alignment to the Program and Portfolio Management Standards (10 minutes) 7. Action items for the next meeting | Confusion seemed to exist as to what requirements were to look like. Mike Reed to upload chapter drafts to bluestep (done) Mike Reed to create several examples of requirements for review and as an example (done).
3 | Closed | 2006-05-15 | 9:30 EDT | 1 HR | 45 min | MR | Michael Reed, Roberta Bonsall, kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Priyesh Gopalakrishnan, Sreedharan Nair, Louisa Andrianopolulou, Nathaniel Barksdale, Raja Sekhar, Michael Hatheway, Cindy Beck, Juan Monroy, Indira Prasad, Rocco Tellier, Lee Towe, Sanina Shen, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, Rachna Sharma, David Cobb, Gethsemani Palacios, Scott Bable, Gaurish Kerkar, Suman Munshi, Mei-Jing Shih | 91-44-24404677 - Gaurish 91 (80) 4193 4333 - Prem Bernard Holmes, Indira Prasad, Gaurish Kerkar, Rocco Tellier, Indira Prasad, Sree Nair, Sanina Shen, | Cindy Beck - notified, PVS Kumar - notified, Scott Bable - notified, Roberta Bonsall - Notified Lee Towe, Prem Udayaavama, David Cobb, Raja Sekhar, Richard Bates, Nathaniel Barksdale, Mei-Jing Shih, Krishma Malladi, Terry Boyd, Priyesh Gopalakrishnan, Michael Hathaway, David Liu, Rachna Sharma, Louisa Andrianopolulou, | Not tracked | Review of requirements for standardization | Agenda 1. Role call (5 minutes) 2. Review of sub team membership (5 minutes) 3. Review of Standards Requirements (45 minutes) 4. Action items for the next meeting (5 minutes) | 1 & 2 Combine items 1 and 2 by doing a role call by team MR to remind team leads that they need to get teams going. (5/16/06) Reinforced the breakdown of the document by sub teams. Unified Project Management Lexicon may not be done in time. Exposre draft of PMI code of conduct received over 3000 comments and is of questionable value. More attention to be paid to existing code of conduct Assignments from the team leads to follow and MR to make assignments if not. (5/16/06) Objective is to have something from each team to discuss at next week's team meeting. MR to create sub team folders for each team. (5/16/06) Next week's meeting has also been moved to 9:30 PM EDT.
4 | Closed | 5/22/2006 Call in info: 1-866-307-3342 Passcode: 384466 | 9:30 EDT | 1 HR | 45 min | MR | Michael Reed, Roberta Bonsall, kumar polisetty, Richard Bates, Bernard Holmes, Terry Boyd, Priyesh Gopalakrishnan, Sreedharan Nair, Nathaniel Barksdale, Raja Sekhar, Michael Hatheway, Cindy Beck, Indira Prasad, Rocco Tellier, Lee Towe, Sanina Shen, Krishna Malladi, David Liu, Cindy Archer-Burton, Prem Udayavarma, Rachna Sharma, David Cobb, Gethsemani Palacios, Scott Bable, Gaurish Kerkar, Mei-Jing Shih, Ganesh Malgikar | 91-44-24404677 - Gaurish KerKar 91 (80) 4193 4333 - Prem Udayavarma 91-98-86897808 Suman Mushi +919885481436 or +914039181520 Raja Sekhar +91-44-42021023 or +91-98405-27704 Priyesh Gopalakrishnan Also, Sanina Shen, Rachna Sharma, Rocco Tellier, Cindy Beck, Mike Reed, David Cobb, Indira Prasad, and Bernard Holmes | PVS Kumar - Notified in advance Scott Bable - Notified in advance Roberta Bonsall, Richard Bates, Terry Boyd, Sree Nair, Nathaniel Barksdale, Michael Hatheway, Lee Towe, Krishna Malladi, Cindy Archer Burton, Mei-Jing Shih, Xiasong Liu | Michael Hathaway, Roberta Bonsall, Scott Bable, Xiasong Liu | Update and Review of Sub Team Work | Agenda 1. Role call (5 minutes) 2. Update from Sub Teams (1 minute each) 3. Review of Core Team Agenda For Face to Face Meeting (5 minutes) 4. Review of Standards Requirements (40 minutes) 5. Action items for the next meeting (5 minutes) | 1. Attendance below 2. Mike to create Sub team email list (completed on 5/23/06). Bernard is reaching out and getting started. Rocco has his team engaged. Raja sent email introduction on Tuesday morning. 3. Still trying to find documents. Looking for examples. Looking for flow chart. Pointed at kick off team meeting presentation and bluestep. Asked for chapters. Pointed to bluestep. Need webinar software - push on PMI. 4. Reviewed agenda for face to face core team meeting. 5. continue to review. Next meeting to follow once we have face to face. Ask for help, guidance from sub team leads, anyone else. Find a place to put pictures of the team. Link to names in project control workbook? Post on bluestep.
5 | Closed | 2006-06-12 | 9:30 PM EDT | 1 hr | 35 Minutes | MR |  |  |  |  | Status Update | Agenda 1. Role call (5 minutes) 2. Update from Sub Teams (1 minute each) 3. Review of Core Team Face to Face Meeting (5 minutes) - New project Name - Project Management Competency Development Framework - Second Edition 4. Review of PMCDF Update project Schedule (10 minutes) 5. Review of Chapter Review Template (10 minutes) 6. Review of requirements (20 minutes) 7. Action items for the next meeting (5 minutes) | Sub team leads - few updates. Still struggling. Asking broad questions or no questions. Send moderator's code to team leads. MR to create requirements and send to team members. Differences between integration and edit still kind of vague. Refer to slide 5. Refer to the work done at face to face. MR to send better examples and instructions. Make it more concrete and less abstract. Reviewed schedule. Reviewed face to face meeting outcome. Trying to get webcast software.
6
7
7
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Issue Log
Action # | Project Or Team | Opened By | Status | Priority | Creation Date | Due Date | Owner | Related Requirement | Issue or Action Item Description | Impact and/or Urgency | Current Status/ Comments | Resolution Date | Resolution Details
1 | Chapter 1 | MR | Open | H | 2016-05-15 | 2006-06-01 | LW | SGUL 3 | Are we changing definition of competency? | Has impacts to Combined Standards Glossary and Unified Lexicon | Review with Lyn Windsor and Core Team
2 | Integration | MR | Closed | H | 2016-05-15 | 2006-06-01 | MR | Integration Sub Team 4 | How much difference is there between draft PPMS and published PPMS | Does it have implications into integration checks | Check with Mike Yinger during face to face | 2006-05-23 | Downloaded final versions from PMI.org and compared . Most differences are in the order of words and some vocabulary changes. We can use drafts to compare
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
52
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
76
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120

## Risk Register
Risk Number | Project or Sub Team | Program Level | Opened Date | Last Update Date | Closure Date | Risk Identification |  |  | Risk Owner | Potentially Impacted Team or Subteams | Risk Assessment |  |  |  | Impact Date | Mitigation Plans (Prevention) (For Red and Yellow Risks Only) | Contingency Plans (Reaction steps) (For Red Risks Only) | Comments | Open/ Closed Status
[6 empty] | Risk Name | IF (describe the event that could occur) | THEN (describe the event's impact) |  |  | Probability of Event Occurring | Impact of Event Occurring | Risk Exposure | Risk Category
1 |  |  | 2006-05-01 | 2006-05-15 | 2006-05-15 | Non Alignment in existing documents | If the existing standards, which we are using as a reference point don't align themselves .. | Then we will be forced to allow a discrepancy in the PMCDF document | MR | All | 3 | 3 | 9 | Quality | 2006-07-30 | Prioritize documents for precedence | If documents are the same priority, appeal to PMI for a differentiation. | We havel also created a prioritized list of reference documents | Open
2 |  |  | 2006-05-01 | 2006-05-15 |  | Lack of volunteers | If we get inadequate participation | schedule could slip or quality could be impacted by lack of sufficient review | MR | All | 2 | 3 | 6 | Quality | 2006-07-01 | Encourage and communicate frequently with team | Solicit new members as necessary | Ok, so far | Closed
3 |  |  | 2006-05-15 | 2006-05-15 | 2006-05-15 | PMI Code Of Conduct Exposure Draft | If the PMI Code of Conduct Exposure Draft varies significantly from the final version… | Alignment of the PMCDF Update, particulary chapter 3, will be very difficult. | MR | Chapter 3 | 4 | 3 | 12 | Quality | 2006-07-01 | Rely primarily on current drart for alignment. | Stay close in contact with Nan and Chris | Exposure Drart received over 3000 comments | Closed
4 | [12 empty] | 0
5 | [12 empty] | 0
6 | [12 empty] | 0
7 | [12 empty] | 0
8 | [12 empty] | 0
9 | [12 empty] | 0
10 | [12 empty] | 0
11 | [12 empty] | 0
12 | [12 empty] | 0
13 | [12 empty] | 0
14 | [12 empty] | 0
15 | [12 empty] | 0
16 | [12 empty] | 0
17 | [12 empty] | 0
18 | [12 empty] | 0
19 | [12 empty] | 0
20 | [12 empty] | 0

## Assumptions
Assumption # | Project | Status | Creation Date | Opened By | Related Risk | Assumption Statement | Assumption Description | Valid | Validated By | Validation Method | Current Status/ Comments | Resolution Details
1 |  | Closed | 2006-05-01 | MR | 1 | Standards documents are in alignment | We assume that the existing reference documents, which we will use as a reference are in alignment with each other | No | Core Team | Supposition | We expect small and insignificant mis alignments in the standards document. | Prioritize and/or escalate issues as they arise
2 |  | Closed | 2006-05-04 | MR |  | PMCDF assumes a project manager with 3 years of experience, managing medium size projeccts, and has just received PMP | We are assuming one skill level. We are not looking at tiers or projgram managers, etc. This framework is to support development of someone who has just become eligible and passed their PMP. | Yes | Core Team | Discussion | Per charter reviewed and renewed in Feb 06. | See statement and description.
3 |  | Closed | 2006-05-15 | MR |  | Assume that exposre drafts of PPMS are similar to Final draft | This assumes we can use draft PPMS documents to create requirements and ensure alignment and do without the published version. | Yes | Mike Reed | Review of published standard (from www.pmi.org) against exposure drafts | Most of the differences are in the order and supplementary material (glossary, index, etc.) | We can use PPMS exposure drafts for the alignment reviews. If questions, PMI members can download a softcopy (unprintable) from www.pmi.org.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Constraints
Constraint # | Project | Status | Creation Date | Opened By | Related Risk | Constraint Statement | Constraint Description | Valid | Validated By | Validation Method | Current Status/ Comments | Resolution Details
1 | PMCDF | Closed | 2006-05-16 | MR |  | Updated PMCDF size increase limit | New PMCDF must be within 20% of the old PMCDF | Yes | Charter | Review
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Dependency Mapping (hidden)
|  | Chapter 1 | Chapter 2 | Chapter 3 | Chapter 4 | Edit Team | HR Team
Document | Integration Point
PMBOK
Current PMCDF
PM Role Delineation Study
PMP Exam Specs
OPM3
PM Career Framework
Unified PM Lexicon/ Combined Standards Glossary
PMP Code of Conduct (existing and exposure draft)
Program and Portfolio Management Standards

## Schedule
Done | Activity | Owner | Planned Start | Planned Finish | Actual Start | Actual Finish | Comments
Initiation Phase
Yes | Kick off meeting | MR | 2006-05-01 | 2006-05-05 | 2006-05-08 | 2006-05-08
Yes | Sub Team Leads Assigned | MR | 2006-05-08 | 2006-05-08 | 2006-05-08 | 2006-05-08
Yes | Sub Team Members Assigned | MR | 2006-05-15 | 2006-05-15 | 2006-05-15 | 2006-05-15 | By role call at 5/15/06 meeting
Planning Phase
Yes | Integration requirements examples | MR | 2006-05-04 | 2006-05-15 | 2006-05-10 | 2006-05-11 | Posted on bluestep
| Sub Team 1 | CAB | 2006-05-08 | 5/26/2006 6/15/2006 | 2006-05-15 |  | Requirements Completed
| Sub Team 2 | RT | 2006-05-08 | 5/26/2006 6/15/2006 | 2006-05-15 |  | Requirements Completed
| Sub Team 3 | NRS | 2006-05-08 | 5/26/2006 6/15/2006 | 2006-05-15 |  | Requirements Completed
| Sub Team 4 | BAH | 2006-05-08 | 5/26/2006 6/15/2006 | 2006-05-15 |  | Requirements Completed
| Comment Template Finalized | MR | 2006-05-08 | 5/26/2006 6/15/2006 | 2006-05-15 |  | Requirements Completed
Control Phase
Yes | Integration Team Meetings | MR | 2006-05-08 | 2006-05-08 | 2006-05-08 | 2006-05-08 | First meeting after kickoff
| Core team Meetings | CC | 2006-05-09 | 2007-05-30 | 2006-05-09 |  | Core only, as scheduled
Yes | Integration Team Meetings | MR | 2006-05-15 | 2006-05-15 | 2006-05-15 | 2006-05-15 | Finalize sub teams and review requirements
Yes | Integration Team Meetings | MR | 2006-05-22 | 2006-05-22 | 2006-05-22 | 2006-05-22 | Review of requirements examples, requirements created, and answer questions.
| Integration Sub Team Leads begin reporting status to Team Lead and Deputy Lead | CAB, RT, NRS, BAH | 2006-05-22 | 2006-08-30 | 2006-05-22 |  | Weekly by email
Yes | Core team Meetings | CC | 2006-05-26 | 2006-05-28 | 2006-05-26 | 2006-05-28 | Face To Face Meetings
Yes | Integration Team Meetings | MR | 2006-06-12 | 2006-06-12 |  |  | Review of requirements examples, requirements created, and answer questions.
| Integration Team Meetings | MR | 2006-06-19 | 2006-06-19
Execution Phase
Yes | Preliminary drafts available | Chapter Teams | 2006-05-16 | 2006-06-01 | 2006-05-26 | 2006-05-28 | At core team face to face meeting
| Updates to chapters based on Face to Face feedback | Chapter Teams | 2006-05-28 | 2006-06-30 | 2006-05-28 |  | Chapter 1 to be delivered on 7/6/06
| Quality teams (Integration and Edit) review of Draft 1 | Edit and Integration | 2006-06-30 | 2006-07-20
| Comments incorporated | Chapter Teams | 2006-07-21 | 2006-08-03
| Core Team Review of Draft 2 | Core Team | 2006-07-28 | 2006-08-03
| Subject Matter Expert Review | SME | 2006-08-04 | 2006-09-04 |  |  | Includes adjudication of SME comments
| Internal Team Review | All reviewers | 2006-08-04 | 2006-09-08 |  |  | Includes review by Integration and Edit teams, in addition to all reviewers
| Comments incorporated | Chapter Teams | 2006-09-04 | 2006-09-15
| Core Team Review and Signoff on Draft 3 | Core Team | 2006-09-11 | 2006-09-19
| Member Advisory Group Review | MAG | 2006-09-20 | 2006-10-11 |  |  | Internal PMI review
| Comments incorporated | Chapter Teams | 2006-10-12 | 2006-10-25
| Core Team Reivew and signoff (face to face) of draft 4 | Core Team | 2006-10-14 | 2006-10-27 |  |  | Exposure Draft
| Exposure draft period | PMI Community | 2006-10-30 | 2007-03-26 |  |  | Includes document parsing for PMI website, receipt of comments, adjudication of comments, and appeals process.
| Appendices created and delivered to PMI | Edit Team | 2006-11-20 | 2007-01-15
| Comments incorporated | Chapter Teams | 2007-03-20 | 2007-04-09
| Core team review and signoff (f2f) on Final Draft | Core team | 2007-03-31 | 2007-04-09
| Publish final document | PMI Community | 2007-04-09 | 2007-07-31 |  |  | Includes final editing, consensus body ballotting and adjudication, and the publishing process (7 weeks).
ClosurePhase
| Non Essential Team Roll off | DPM | 2006-09-20 | 2006-10-27 |  |  | Scope to be determined
| Lessons learned | DPM | 2007-04-10 | 2007-05-21
| Non Core Team Roll off | DPM | 2007-04-10 | 2007-05-21
| Celebration of success | DPM | 2007-06-13 | 2007-09-04
| Core Team Roll off | DPM | 2007-06-13 | 2007-06-19
| Signing Ritual | DPM | 2007-08-01 | 2007-08-28

## Status Report
Date | Integration Team | Sub Team 1 | Sub Team 2 | Sub Team 3 | Sub Team 4
2006-05-22 | ▪ Team meeting on 5/22 ▪ Created and reviewed requirements example. 0.3 ▪ Created first draft of chapter review template ▪ Core team face to face meeting ▪ Created sub team committees to help sub teams send email via bluestep | ▪ Finalized team membership | ▪ Finalized team membership ▪ Began creating requirements | ▪ Finalized team membership ▪ Sent kickoff meeting notice to sub team | ▪ Finalized team membership ▪ Following up on kickoff email with phone calls
2006-05-29 | ▪ Team meeting on 6/12 ▪ Reviewed new schedule▪ Created first draft of chapter review template ▪ Core team face to face meeting ▪ Created sub team committees to help sub teams send email via bluestep | ▪ Still struggling | ▪ Still struggling | ▪ Still struggling | ▪ Still struggling
2006-06-12 | ▪ Team meeting on 5/22 ▪ Created and reviewed requirements example. 0.4 ▪ Reviewed chapter review comments template ▪ Reviewed document flow and new schedule ▪ MR to write 10 to 12 requirements for each document | ▪ Still struggling | ▪ Still struggling | ▪ Still struggling | ▪ Still struggling

## Change Management
Change Management Log
Change Control # | Project | (Sub) Team Lead | Date Submitted | Change Type | Brief Description of Change | Specific Changes | Reason For Change | Project Manager Comments | Impact to Program Scope: Increasing or Decreasing Scope? | Impact to Program Critical Path? | Other Projects Impacted? | Status | PRD Version If Approved | Notes Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Stakeholder Analysis (hidden)
Stakeholder # | Organization/Team | Team/ Individual Name | Participants if Team | Description (Roles and Responsibilities) | Stakeholder Type | Hopes | Fears | Communication Needs | Frequency / Date | Comments
1
2
3
4
5
6
7
8
9
10

## Lessons Learned
Lesson Number | Lesson | Advice for Future Projects
1 | Integration concepts not well understood at first | Provide examples and/or thought starters for process earlier
2 | Meeting logistics not as good as it could be | Be sure moderator has moderator code. Make sure a second person has moderator code.
3 | Moving meeting time without sufficient notice causes problems | With a global volunteer group moving a meeting should occur at least 48 hours before the meeting.
4 | IM window during phone calls works better than just email, especially with team members that must be dialed into meetings. | Use an IM client during meetings. Agree on one and publish that you will use it.
5 | It takes 2 to 3 weeks to get team leads engaged in most cases. Work and life inhibit immediate spin up and absorption of tasks to be done, team members involved, etc. | Allow more time in schedule for team lead or sub team lead start up.
6 | Writing requirements has been a huge struggle. | Have this done by a smaller, senior team for others to use.
7
8
9
10

## Risk Guidelines (hidden)
Impact of Event Occurring
4
3
2
1
1
2
3
4
5
Probability
of Event
Occurring
R
R
R
R
R
Y
Y
Y
Y
Y
Y
G
G
G
G
G
G
G
High
Med
Low
Risk Exposure
R
Y
G
Risk Exposure
5
R
R
Y
G
R
G
G
Probability of Event Occurring
Scale
Description
5
Almost Certain
4
Highly Probable
3
Probable
2
Possible
1
Improbable
Probability
80-100%
60-80%
40-60%
20-40%
0-20%
Probability of Event Occurring
Scale
Description
5
Almost Certain
4
Highly Probable
3
Probable
2
Possible
1
Improbable
Probability
80-100%
60-80%
40-60%
20-40%
0-20%