HITSP-CCHIT Joint Working Group
                                                                     
Meeting Results

	Meeting Name
	HITSP-CCHIT Joint Working Group Internal Meeting

	Meeting Date and Time: 
	January 3rd, 2007  11:00 AM ET  

	Location:
	Teleconference

	Objectives: 
	Internal meeting of the HITSP-CCHIT JWG 

	Next Meeting Scheduled:
	January 11th at 6:45pm Dial-in: 800-446-1162   Passcode: 751900


	Agenda 


General Announcements/Topics

· Review HITSP & CCHIT documents from 12/20/06 inaugural call with CCHIT (attached) 
· Goals, objectives and expectations of the work group 
· Work in progress 
· Development of joint timeline 
· Path forward on lab standards for 2008 
	Decisions and Actions


Opening of Meeting & Remarks
Jamie Ferguson, chair of the JWG, welcomed the group and informed the group about the agenda for the day. The objective was to focus on goals, objectives and expectations for the workgroup on the part of the Panel membership. Also on the agenda was the discussion on the lab standards. Jamie also asked if there were any other areas to focus on. The following were raised:

· Lyle Schofield would like more information about the interactions and integrated timeline between the 2 organizations. Also wants to know what the HITSP process is for determining what this team does. 
· Peter Elkin commented that if the group is using a guiding principle to make decisions, they’ll be better able to make those decisions consistently as they come along. It’ll be important to prioritize activities because real industry needs in certain areas need to be pushed forward more than others. If priorities are identified up front, the group will know what to push first, and missing areas can be coordinated. 

Discussion on Goals, objectives and expectations of the work group
Jamie moved the discussion to the agenda item: Goals and objectives of the JWG. He went through the power point presentation that was used in the inaugural JWG external meeting and asked for comments and discussion of the listed objectives for the group.  Group gave additional points, clarifications and considerations:

· Expectation that HITSP and CCHIT can bring attention to areas that they encounter gaps in standards that need to be bridged, and work together on a resolution timeline

· CCHIT does not have a solid liaison relationship with SDO’s and so for CCHIT to be influential in prioritizing SDO work, those liaison relationships have to be developed or handled through HITSP

· Need to coordinate and communicate about issues with Interoperability Specifications as well as gaps in standards

· Need to clarify the relationship between HITSP and CCHIT 
· The updated goals and objectives will be distributed to the group

Work in progress: Path forward on lab standards for 2008
· Group decided to discuss lab next, however there was a comment made to add another item for the group to discuss: CCR, CCD - put on agenda for future discussion. How soon will that get done and be aware that CCHIT will need to reference what HITSP comes out with.
· Charles’ response was that there is unanimous support for CCD and they’re waiting for the ballot to go through; expect to have a specification unless there are major negative ballots. Should have a revised CE spec by April – that’s the plan and the consensus by HITSP. Intent is to provide a mapping of CCD which will be part of the spec.  HITSP agreed to this back in October.
· Started discussion on the Lab Transition Path Options document. Document shows the transition from year to year to a harmonized ELINCS-HITSP specification for 2008 and beyond, with increasingly greater coding required each year.
· Since there was no longer any time to continue the discussion, it was suggested that the JWG have 2hr meetings once a month. It was also suggested that since CCHIT needs to make a decision about the lab standards, there’d be a follow-up meeting to complete the lab standards discussion.

· ACTION:  Jamie and Sarah will publish a schedule of meetings for the next month 
· ACTION: Sarah will send out a poll by email to find the best time for the meeting to discuss the Lab transition path options 
Participants
	Attendee, Project Role
	Org.
	Present

	Robert Barker
	NextGen
	X

	Chris Carr
	RSNA
	

	Howard Clark
	DICOM
	X

	Michelle Deane
	ANSI
	X

	Gary Dickinson
	CentrifyHealth
	X

	Peter Elkin
	Mayo Clinic
	X

	Joseph Holtschlag
	MassPRO
	

	Jamie Ferguson
	Kaiser Permanente
	X

	Gwen Lohse
	CAQH
	

	Kathleen Mahan (Weigang Li sat in for Kat Mahan)
	SureScripts
	X

	Glenn Marshall
	Siemens
	X

	Don Mon
	AHIMA
	X

	Charles Parisot
	GE Healthcare
	X

	Sarah Quaynor
	GSI Health
	X

	Rick Reeves 
	CPSI
	X

	Maria Rudolph
	American College of Cardiology
	X

	Dan Soule
	Cerner
	X

	Steve Steindel
	CDC
	X

	Lyle Schofield
	CodeRyte
	X


[image: image1.png]









Page 2

