| Activity | Description of Activity | Responsible | Dates |
| --- | --- | --- | --- |
| Meetings |  |  |  |
| TC Face to Face I | TC’s meet to draft Interoperability Specifications Four Points Sheraton - Baltimore | TCs and Performance Team | TC Leadership: July 17 TC: July 18 - 20 |
| TC Face to Face II | TC’s meet to finalize Interoperability Specifications Chicago Hilton Garden Inn | TCs and Performance Team | TC Leadership: August 14 TC: August 15 – 17 Project team only August 18 |
| TC Face to Face III (Tentative) | TC’s meet to update Interoperability Specifications post Test and Comment | TCs and Performance Team | TBD??? |
| Board Meeting | Board meets to review HITSP progress | Design Team Lead | September 8 |
| Panel Meeting | Panel meets to approve Interoperability Specifications | Design Team Lead | September 20 |
| Other Deliverables |  |  |  |
| Interoperability Specifications |  |  |  |
| Draft Interoperability Specifications | Technical Committees meet to finalize the draft IS for inspection testing | TCs & Performance Team | July 5 – August 17 COB August 18 – Project team |
| Panel Review I: Comment and/or Inspection Test of IS | Interoperability Specification is reviewed and inspection tested by the HITSP Panel and public | Design Team Lead Posts, Performance Team manages comments | August 18 - 30 |
| Update I: Address Comments from Review / Inspection Test | Technical Committees update Interoperability Specifications | TCs & Performance Team | August 31 – September 12 |
| Panel Review II: Review and comment of IS updates | Posted to HISTP.org and review and comment thru the 19th – comment review period closes the 20th | Design Team Lead Posts, Performance Team manages comments | September 13 – 19 |
| Panel Approval: Approval IS | HITSP Panel Approves IS | Panel | September 20 |
| Update II: TCs Finalize Interoperability Specifications | TC’s finalize IS for delivery to ONC | TCs & Performance Team | September 20 – 25 COB |
| Finalize Interoperability Specifications | TCs update based on panel comments | Project Management Team | September 26 – 28 COB |
| Deliver Interoperability Specifications | SOW Ref # 9 | Project Management Team | Friday, September 29, 2006 |

HITSP Schedule July – August, 2006