| Main Project Milestones | Time limit | Directives (Ed. 2014) |
| --- | --- | --- |
| Circulation of Result on Vote for NP (RVN) | Start of the time counter | Part 1 - 2.1.6 |
| First Working Draft | 6 months | Part 1 - 2.1.6 |
| First Committee Draft (CD) | 12 months | Part 1 - 2.1.6 |
| Committee Draft for Vote (CDV) | 24 months | Part 1 - 2.1.6 |
| Final Draft International Standard (FDIS) | 33 months | Part 1 - 2.1.6 |
| Publication of the International Standard | 36 months | Part 1 - 2.1.6 |
| Maintenance of the International Standard | Project finished before the stability date | IEC Suppl. - 2.9.3.2 |

| Action Description | Action by | Form | Time limit | Directives (Ed. 2014) |
| --- | --- | --- | --- | --- |
| Circulation of New Work Item Proposal (NP) | TC/SC Secretary | Form NP |  |  |
| Vote on NP | P-members of TC/SC |  | 3 months | Part 1 - 2.3.4 |
| Research of experts | TC/SC Secretary |  | 4 weeks after close of vote on NP | IEC Suppl. – 2.3.5 |
| Circulation of Result on Vote for NP (RVN) | TC/SC Secretary | Form RVN | 4 weeks after close of vote on NP | IEC Suppl. – 2.3.6 |
| Availability of first Working Draft | TC/SC Workgroup | iecstd | 6 months after circulation of RVN | Part 1 - 2.1.6 |
| Availability of first Committee Draft (CD) | TC/SC | Form CD | 12 months after circulation of RVN | Part 1 - 2.1.6 |
| Comments on CD | P-members and O-members of TC/SC |  | 2, 3, or 4 months as agreed by TC/SC | Part 1 – 2.5.2 & 2.5.4 |
| Compilation of comments on CD (CC) | TC/SC Secretary | Form CC | 4 weeks after close of comments | Part 1 - 2.5.3 |
| Define stability date | TC/SC Secretary to include in "FormCDV.dot" |  | Stability date from 3 to 12 years | IEC Suppl. - 2.6.1 |
| Send CDV to CO for translation and circulation | TC/SC Secretary | Form CDV | 24 months after circulation of RVN | Part 1 - 2.1.6 & AC/21/2012 |
| Translation of Committee Draft for Vote (CDV) | Central Office (CO) |  | 2 months after receipt of the CDV | Part 1 - 2.6.1 & AC/21/2012 |
| Comment and Vote on CDV | All NCs (P-members mandatory) |  | 3 months (5 months on request) | Part 1 - 2.6.1 AC/21/2012 |
| Editing of CDV | Central Office (CO) |  |  |  |
| Result of Vote on Committee draft (RVC) | TC/SC Secretary (including resolved comments) | Form RVC | 3 months after close of vote on CDV | Part 1 - 2.6.5 |
| Send FDIS to CO for translation and circulation | TC/SC Secretary (Decision by Chairman) | Form FDIS | 4 months after close of vote on CDV | Part 1 - 2.6.6 |
| French translation of FDIS | Central Office (CO) |  | 1 week or 2 months max. after receipt of the FDIS | SMB Decision 150/20 |
| Editing and circulation of FDIS | Central Office (CO) |  | 3 Months after FDIS accepted by CO | Part 1 - 2.7.1 |
| Availability of FDIS | TC/SC |  | 33 months after circulation of RVN | Part 1 – 2.1.6 |
| Vote on FDIS | All NCs (P-members mandatory) |  | 2 months | Part 1 - 2.7.1 |
| Report of voting on FDIS (RVD) | Central Office prepares and circulates RVD | Form RVD | 2 weeks after close of vote on FDIS | Part 1 - 2.7.5 |
| Publication of IS | Central Office (CO) |  | 1.5 month after circulation of RVD | Part 1 - 2.8.1 |
| Availability of International Standard | TC/SC & Central Office |  | 36 months after circulation of RVN | Part 1 - 2.1.6 |
| Maintenance of the International Standard | TC/SC Secretary | Form RR | Project finished before the stability date | IEC Suppl. - 2.9.3.2 |
| General Purpose Form (INF, RM, DC, Q) | TC/SC Secretary | iecform |  |  |

Summary of actions and time limits for the development of a Technical Specification (TS)

| Action Description | Action by |  | Time limit | Directives (Ed. 2014) |
| --- | --- | --- | --- | --- |
| Circulation of New Product Proposal (NP) | TC/SC Secretary | Form NP |  | Part 1 - 3.1.1.1 & 2.3 |
| Vote on NP | P-members of TC/SC |  | 3 months | Part 1 - 2.3.4 |
| Circulation of Result on Vote for NP (RVN) | TC/SC Secretary | Form RVN | 4 weeks after close of vote on NP | IEC Suppl. – 2.3.6 |
| Development of Draft TS (DTS) | TC/SC Working Group |  |  | Part 1 - 3.1.1.1 & 2.4 |
| French translation of DTS | French NC |  | 1 week or 2 months max. after receipt of the DTS | IEC Suppl – E.3.1.1 & E.3.1.3 |
| Circulation of DTS | TC/SC Secretary | Form DTS |  | Part 1 - 3.1.1.1 & 2.5 |
| Vote on DTS | All NCs (P-members mandatory) |  | 3 months | Part 1 - 3.1.1.1 & 2.5 |
| Result of Vote on DTS (RVC) | TC/SC Secretary (including resolved comments) | Form RVC | 3 months after close of vote on DTS | Part 1 - 2.6.5 |
| Provide final TS to Central Office | TC/SC Secretary | iecstd | 4 months after close of vote | Part 1 – 3.1.2 |
| Editing and Distribution of TS | Central Office |  |  |  |
| Document Maintenance | TC/SC | Form RR | New edition 3 years after previous publication | Part 1 - 3.1.3 |

Summary of actions and time limits for the development of a Publicly Available Specification (PAS)

| Action Description | Action by |  | Time limit | Directives (Ed. 2014) |
| --- | --- | --- | --- | --- |
| Circulation of Draft PAS (DPAS) | TC/SC Secretary | Form DPAS |  | AC/48/2007 |
| Vote on PAS | All NCs (P-members mandatory) |  | 2 months | IEC Suppl. Annex SO |
| Result of Vote on PAS (RVDPAS) | TC/SC Secretary (including resolved comments) | Form RVDPAS | 3 months after close of vote on PAS | Part 1 - 2.6.5 |
| Editing and Distribution of PAS | Central Office |  |  |  |
| Document Validity | TC/SC |  | 3 years, expendable once to 3 other years | Part 1 - 3.2.4 |

Summary of actions and time limits for the development of a Technical Report (TR)

| Action Description | Action by |  | Time limit | Directives (Ed. 2014) |
| --- | --- | --- | --- | --- |
| Circulate a Committee Draft (optional) | TC/SC | Form CD |  |  |
| Comments on CD | P-members and O-members of TC/SC |  | 2, 3, or 4 months as agreed by TC/SC |  |
| Proposal of Draft Technical Report (DTR) | TC/SC Secretary | Form DTR |  | Part 1 - 3.3.1 |
| French translation of DTR | French NC |  | 1 week or 2 months max. after receipt of the DTS | IEC Suppl – E.3.1.1 & E.3.1.3 |
| Vote on DTR | P-members |  | 2 months | IEC Suppl. Annex SO |
| Result of Vote on DTR (RVC) | TC/SC Secretary (including resolved comments) | Form RVC | 3 months after close of vote on DTR | Part 1 - 2.6.5 |
| Provide final TR to Central Office | TC/SC Secretary | iecstd | 4 months after close of vote | Part 1 - 3.3.2 |
| Editing and Distribution of TR | Central Office |  |  |  |
| Document Maintenance / Withdrawal | TC/SC | Form RR | "regularly" | Part 1 - 3.3.3 |